|  | ACTIONS | PERFORMANCE MEASURE | MILESTONES |  |  |  | NOTES |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2022/2023 |  | 2023/2024 | 2024/2025 |  |
|  |  |  | Target | Status as of Q4 |  |  |  |
| GOAL 1: Indigenous Representation | Action 1.1: Review all job descriptions to remove systemic barriers and reflect appropriate non-inflated education and experience requirements. | # of job descriptions (JDs) reviewed # of applicants on job postings Increased use of equivalencies | 25% (22) of JDs reviewed | Job Description Guide Launched A total of 10 job descriptions were updated in 22-23 for Housing NWT . | 25% (22) of JDs reviewed | 50% (43) of JDs reviewed |  |
|  |  |  |  |  |  | 10% increase in applicants |  |
|  | Action 1.2: Hiring managers complete training on the staffing process, recruitment programs and understanding systemic and unconscious racism and bias within the hiring process. | # of hiring managers who complete the training | Training launch | Hiring Managers training launched 4.6% of employees have completed training | 20% completion | 40% completion |  |
|  | Action 1.3: Review Indigenous eligibility lists for pre-qualified candidates prior to initiating a job competition. | # of positions filled without a competition Increase of Indigenous hires within department Increased number of candidates added to database | Launch of eligibility database | Under development | 3 positions are filled with eligibility lists | 5 positions are filled with eligibility lists |  |
| GOAL 2: Indigenous Leadership | Action 2.1: Ensure that all employees complete Living Well Together: Indigenous Cultural Awareness and Sensitivity Training. | # of employees who have completed the training | 60% of employees have completed training | Completion Rate – 56.9% | 80% of employees have completed training | 90% of employees have completed training |  |
|  | Action 2.3: Ensure all employees complete the Equitable Workplace: Cultivating Attitudes of Anti-Racism and Allyship Training. | # of employees who have completed the training # of sessions available | 7% of employees have completed training | Equitable Workplace: Completion Rate – 4.6% Unconscious Biases: Completion Rate – 1.8% | 10% of employees have completed training | 15% of employees have completed training |  |
|  | Action 2.4: Ensure employees complete exit interview process that includes questions about employee experiences with bias, racism, discrimination, harassment and cultural insensitivity. | # of exit interviews completed with employees who leave their position | Department of Finance develops exit interview process | Under development | Department of Finance develops exit interview process | 15% of departing employees complete an exit interview |  |
|  | Action 2.5: Ensure Indigenous employees are aware of and apply to the Indigenous Management Development and Training Program (IMDTP), and that it is fully subscribed. | # of employees accessing program | 1 employees from department have accessed IMDTP | 2 employees has accessed IMDTP | 3 employees from department have accessed IMDTP | 3 employees from department have accessed IMDTP |  |
|  | Action 2.5: Access Indigenous mentorship program for informal on-the-job training. | # of employees accessing program # of succession plans | Department of Finance develops and promotes Indigenous Mentorship Program | Under development | Department of Finance develops and promotes Indigenous Mentorship Program | 10% of Indigenous employees are participating in the program in some capacity |  |
|  | Action 2.5: Support employees to identify career pathways and training needs in their Learning and Development Plan as a part of the Performance Development process. | # of indigenous employees who identify career pathways and training needs in their Learning and Development Plan | Department of Finance will create resources for employees to identify career pathways in their Learning and Development Plan | Under development | Department of Finance will create resources for employees to identify career pathways in their Learning and Development Plan | 15% of employees have identified a career path |  |
|  | Action 2.5: Work with HR on succession planning with a focus on Indigenous employee development. | # of Indigenous employees identified for succession planning | Department of Finance creates succession planning guide; department works with HR to develop Succession Plan | Under development | Department of Finance creates succession planning guide; department works with HR to develop Succession Plan | 10% of managers have identified Indigenous employees within succession plans |  |
|  | Action 2.6: Use of the Indigenous Career Gateway Program. (ICGP). | # of ICGP candidates hired | Minimum of 1 position filled using ICGP | 0 positions filled using ICGP | 2 positions filled using ICGP | 3 positions filled using ICGP |  |
|  | Action 2.6: Promote the use of transfer assignments and cross-training to encourage mobility and development for Indigenous employees. | # of employees on transfer assignments (TA) or Secondments # of Indigenous employees within Middle and Senior management roles | Minimum of 5% of TAs filled by Indigenous employees | At the end of 22-23, there were 9 indigenous individuals that took on transfer assignments throughout the year. | 5% of TAs filled by Indigenous employees 22,2% of TA’s filled by Indigenous employees | 5% of TAs filled by Indigenous employees |  |

| Housing NWT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| INDIGENOUS EMPLOYMENT TARGETS |  |  |  |  |  |
|  |  | CURRENT (March 31, 2023) | SHORT-TERM TARGETS (By March 31, 2024) | MEDIUM-TERM TARGETS (By March 31, 2026) | LONG TERM TARGETS (By March 31, 2028) |
| Staffed positions |  |  |  |  |  |
| All filled positions |  | 111 | 106 | 106 | 106 |
| Indigenous Aboriginal employees |  | 38 | 39 | 40 | 43 |
| Net Increase Target |  | -1 | +8 | +1 | +3 |
| Percentage |  | 34.24% | 36.8% | 37.7% | 40.6% |
| Indigenous Aboriginal employees by job classification |  |  |  |  |  |
| Senior Management |  |  |  |  |  |
| Total employees |  | 14 | 12 | 12 | 12 |
| Indigenous employees (#) |  | 4 | 4 | 4 | 5 |
| Net Increase Target |  | - | - | - | +1 |
| Indigenous employees (%) |  | 28.6% | 33.3% | 33.3% | 41.7% |
| Middle management |  |  |  |  |  |
| Total employees |  | 24 | 20 | 20 | 20 |
| Indigenous employees (#) |  | 7 | 7 | 7 | 8 |
| Net Increase Target |  | - | - | - | +1 |
| Indigenous employees (%) |  | 29.2% | 35.0% | 35.0% | 40% |
| Positions Requiring University Equivalency |  |  |  |  |  |
| Total employees |  | 23 | 33 | 33 | 33 |
| Indigenous employees (#) |  | 8 | 12 | 12 | 13 |
| Net Increase Target |  | - | +4 | - | +1 |
| Indigenous employees (%) |  | 34.8% | 36.4% | 36.4% | 39.4% |
| Positions Requiring University/Trade Equivalency |  |  |  |  |  |
| Total employees |  | 28 | 31 | 31 | 31 |
| Indigenous employees (#) |  | 8 | 11 | 11 | 11 |
| Net Increase Target |  | - | +3 | - | - |
| Indigenous employees (%) |  | 28.6% | 35.5% | 35.5% | 35.5% |
| Positions Requiring High School Equivalency or No Formal Education |  |  |  |  |  |
| Total employees |  | 6 | 10 | 10 | 10 |
| Indigenous employees (#) |  | 4 | 5 | 6 | 6 |
| Net Increase Target |  | - | +1 | +1 | - |
| Indigenous employees (%) |  | 66.7% | 50.0% | 60.0% | 60.0% |