## PCRA
GNWT Project Complexity and Risk Assessment Worksheet
| Project Name: | [Project Name]
| Project Description: | [Brief description of project purpose]
| Completed By: | [The person or team completing the worksheet]
| Date Completed: | [YYYY-MM-DD]
| Instructions: | To complete this worksheet, fill out Column D "Score" with values 1 to 5 in each section below. Using Column E "Documentation/Notes", to note any comments or rationale behind your score. A results summary follows the sections.
1. Project Characteristics (11 Questions)
Num | Question | Options | Score | Documentation/Notes
1 | What is the total budget request for this project? | 1 - $50,000 or less 2 - $50,000 to $250,000 3 - $500,000 to $1,000,000 4 - $1,000,000 to $3,000,000 5 - $3,000,000 or more
2 | What percentage of the overall project budget is for procurement? | 1 - 0% 2 - 1% to 25% 3 - 26% to 50% 4 - 51% to 75% 5 - More than 75%
3 | Relative to the average project in your organization, which of the following adjectives describes the total budget of this project? | 1 - Smaller 3 - Average 5 - Larger
4 | How many people are required to complete this project at its peak activity? Note: People can be part-time or full-time on the project, including GNWT employees and individual contractors, but excluding vendor-supplied work teams. | 1 - 5 or less 2 - 6 to 10 3 - 11 to 25 4 - 25 to 50 5 - More than 50
5 | From project initiation to project implementation, what is the expected duration of the project? Note: Use definitions from 'A Guide to the Project Management Body of Knowledge' for initiation and implementation | 1 - 6 months or less 2 - 6 to 12 months 3 - 12 to 24 months 4 - 24 to 36 months 5 - More than 36 months
6 | Horizontal (i.e. cross-departmental or cross-agency) scope: How many sponsoring or funding departments or agencies are involved? | 1 - Only involves one department or agency 2 - Involves two departments/agencies 3 - Involves three department/agencies 4 - Involves four department/agencies 5 - Involves more than four department/agencies
7 | Project Reach The outcome of this project changes or directly affects the following: | 1 - One business process 2 - Multiple processes within a division 3 - Multiple divisions 4 - One entire department 5 - Multiple departments
8 | In supporting the achievement of the expected outcomes, how many of the following criteria apply to the costing model? a) The source of funds has been identified. b) The funds are committed (i.e. authority to spend). | 1 - Both criteria are met 3 - One criterion is met 5 - Neither criteria is met
9 | Is the project susceptible to time delays? Time delays can have a number of causes, such as the following: a) Changes in technology; b) Requirements of participating organizations; c) Seasonal considerations; d) The need for policy approvals; and e) External influences. | 1 - Not suspectible to time delays 3 - Moderately susceptible - delays would have minor effects on schedule 5 - Highly susceptible - delays would have major effects on schedule and could be critical
10 | Does public perception influence the manner in which the project is conducted? | 1 - No 5 - Yes
11 | Do health and safety requirements add significant complexity to the requirements of this project? | 1 - No 5 - Yes
| 11 Questions | 0 Responses | -
2. Strategic Management (2 Questions)
Num | Question | Options | Score | Documentation/Notes
12 | How critical is the project to department, agency or program's key outcomes? | 1 - The project is critical to the department, agency or program's outcomes 3 - There is good alignment with indirect contribution to the outcomes of the department, agency or program 5 - There is weak alignment with the outcomes or the outcomes have not been established
13 | To what degree is the department's management and relevant stakeholders aware of the project? | 1 - There is consistent, clear and comprehensive awareness of the project at all relevant levels 3 - There is good general awareness of the project, its implications and its budget 5 - There is minimal awareness of the project in relevant levels of the organization
| 2 Questions | 0 Responses | -
3. Procurement Risks (4 Questions)
Num | Question | Options | Score | Documentation/Notes
14 | Will the project required products, goods or services be supplied in a timely manner by an appropriate vendor? | 1 - Products, good and services can be readily supplied in a timely manner 2 - Potential slippage of project schedule may be due to procurement complexity or vendor challenges 3 - The project deliverables, schedule or budget may be seriously affected by limited qualified bidders, significant RFP delays or extended challenges
15 | Contracting capabilities How many of the following statements are true? a) Personnel supporting this project have expertise in writing specifications or RFPs/SOWs. b) Personnel supporting this project have subject-matter expertise in the goods or services being procured. c) There is a robust departmental process for reviewing all awarded contracts. | 1 - All statements are true 2 - One statement is true 3 - None of the statements are true
16 | Number of contracts How many separate contracts associated with key deliverables are planned for this project? | 1 - One contract 2 - Two contracts 3 - Three contracts 4 - Four contracts 5 - Five or more contractrs
17 | Contract management How many of the following statements are true? a. The personnel who wrote the contract are involved in the management of the contract. b. There is a standardized acceptance process for the review of the completion of contracts (e.g. peer reviewing or review of the completion of deliverables). c. The lines of communication between the contract authority and the contractor are well-defined and regularized. d. There is a standardized process for reporting progress (e.g. punctual evaluation or regular meetings). e. There is a mechanism in place to address any contractual disagreements between parties regarding the completion of a contract. | 1 - All statements are true 2 - Four statements are true 3 - Three statements are true 4 - Two statements are true 5 - One or none of the statements are true
| 4 Questions | 0 Responses | -
4. Human Resource Risks (3 Questions)
Num | Question | Options | Score | Documentation/Notes
18 | Does your organization anticipate a shortage of available personnel with appropriate skills during a significant period of the project? | 1 - No 5 - Yes
19 | What is the predicted stability of the project team? Consider the following criteria: a) The project team has previously worked together. b) A low rate of turnover is expected. c) It is expected that a suitable replacement will be readily available. | 1 - All three criteria are met 2 - Two of the three criteria are met 4 - One of the three criteria is met 5 - None of the three criteria are met
20 | Knowledge and Experience Consider the following criteria: a) The project will use a proven approach b) This type of project has been done before in the GNWT. c) The project will use resources that have been applied to this type of project before. | 1 - All three criteria are met 2 - Two of the three criteria are met 4 - One of the three criteria is met 5 - None of the three criteria are met
| 3 Questions | 0 Responses | -
5. Business Risks (3 Questions)
Num | Question | Options | Score | Documentation/Notes
21 | Describe the overall effect of this project on the organization: | 1 - Project will fit with current departmental or agency processes, use existing workforce and skills, and not require substantial changes to technology and other infrastructure. 3 - Some changes to processes, staffing models or technology will be required 5 - Significant restructuring of business processes staffing requirements, partner relationships and infrastructure will be required.
22 | Does the project have a change management plan? | 1 - Change Management will be required and a CM Plan has been prepared. Alternatively, there is no significant change management required. 3 - Change Management will be required and preparation of a CM Plan is incorporated or included in the Project Plan. 5 - Change Management will be required but there are no plans to establish a CM Plan.
23 | What level of complexity is introduced to ensure that this project complies with relevant policy requirements, such as those regarding security, accessibility, common look and feel standards for the Internet, and management of government information? | 1 - The project fully conforms with all applicable policies. Alternatively, the project is not subject to any of these policies. 3 - There are some challenges associated with policy requirements, but the project team is adequately equipped to address these. 5 - There is a lack of confidence that policy requirements can be met on schedule and within the budget.
| 3 Questions | 0 Responses | -
6. Project Requirements (11 Questions)
Num | Question | Options | Score | Documentation/Notes
24 | How many of the following statements are true? a) The project solution requires a high degree of availability. b) The project solution requires customization beyond normal configuration. c) The project solution requires a high degree of performance quality. d) The project solution requires a high degree of reliability. Note: “Project solution” is the major output that the project will deliver. | 1 - None of the statements are true 2 - One of the statements is true 3 - Two of the statements are true 4 - Three of the statements are true 5 - Four of the statements are true
25 | In defining project requirements, how many of the following statements are true? a) The requirements can be defined with very few people b) The requirements can be defined in a short period of time c) There is a small number of individual requirements to define d) The requirements do not require a high degree of detail | 1 - Four of the statements are true 2 - Three of the statements are true 3 - Two of the statements are true 4 - One of the statements is true 5 - None of the statements are true
26 | Have feasibility studies been conducted, and is there confidence in the assumptions made in the feasibility studies? Note: Prototypes or proof of concept exercises are included as feasibility activities. | 1 - Feasibility studies are not required, because none of the requirements are technically difficult to implement. 2 - Feasibility studies were conducted and there is confidence in the assumptions made. 4 - Feasibility studies were conducted but there is not complete confidence in the assumptions made. 5 - Feasibilities studies were necessary but not conducted,
27 | Indefinable Requirements (Known Unknowns) What percentage of tasks cannot be fully defined until the completion of previous tasks? Note: These are tasks that may be understood but cannot be documented in detail due to dependency on results from a previous task. | 1 - 10 per cent 2 - 20 per cent 3 - 30 per cent 4 - 40 per cent 5 - >40 per cent
28 | To what extent are the project’s requirements clear, completed, and communicated? | 1 - All requirements are clear, complete and communicated. 3 - Up to 10 per cent of total requirements are not complete or are undocumented. 5 - More than 10 per cent of total requirements are not complete or are unclear.
29 | Stability of project requirements How many of the following project requirement characteristics are expected to remain stable? a) quality b) functionality c) schedule d) integration e) design f) testing Note: Project characterisitics should be expected to remain stable if the project requirements are stable. | 1 - All of the project requirement characteristics are expected to remain stable. 2 - Five of the six project requirement characteristics are expected to remain stable. 3 - Four of the six project requirement characteristics are expected to remain stable. 4 - Three of the six project requirement characteristics are expected to remain stable. 5 - Two or less of the project requirement characteristics are expected to remain stable.
30 | Are any other projects dependent on outputs or outcomes of this project? | 1 - No 5 - Yes
31 | Are outcomes of this project dependent on the outputs and/or outcomes of any other projects? | 1 - No 5 - Yes
32 | What degree of integration with other projects, systems, infrastructure, or organizations is required? | 1 - There are few complex integration requirements; activities to specify integration are included in the project management plan. 3 - There is adequate understanding and planning for integration. 5 - There are highly complex or numerous integration requirements and insufficient planning of required activities.
33 | Relative to the average project in your organization, which of the following adjectives describes the number of tasks, elements, or deliverables in the work breakdown structure? | 1 - Small 3 - Medium 5 - Large
34 | Resources What is the effect on the project of the requirement for scarce resources or resources that are in very high demand? Note: Resources can be internal or external to the government and can be people, goods, or services. If a resource is scarce internally but available externally, then the resource is not considered scarce. | 1 - No scarce resources are required or not applicable. 2 - The project will incur minor delays or minor cost overruns due to scarcity of resources. 3 - The project will incur moderate delays or moderate cost overruns due to scarcity of resources. 4 - The project will incur significant delays or significant cost overruns due to scarcity of resources. 5 - The success of the project is critically dependent on scarce resources.
| 11 Questions | 0 Responses | -
| Project Name: | [Project Name]
| 1. Project Characteristics (11 Questions) | -
| 2. Strategic Management (2 Questions) | -
| 3. Procurement Risks (4 Questions) | -
| 4. Human Resource Risks (3 Questions) | -
| 5. Business Risks (3 Questions) | -
| 6. Project Requirements (11 Questions) | -
| Total Project Complexity and Risk Score: | -
| Percent Complete: | 0%
| ICT Capital Funding Process Required? | Finish worksheet
| Recommended Number of Project Management FTEs: | Finish worksheet
| Recommended Gating Model: | Finish worksheet