## Risks
ID | Risk Statement | Risk Details | Owner | Category | Original Likelihood | Original Impact | Residual Likelihood | Residual Impact | Original Value | Residual Value | Risk Response | Current Responses
1 | Project management resources unavailable |  |  | Human Resources | Likely | High | Likely | High | 16 | 16 | Mitigate
2 | Product integration not possible |  |  | Requirements | Possible | High | Remote | High | 12 | 4 | Accept
3 | Not ready for launch date |  |  | Schedule | Possible | Medium | Unlikely | Low | 9 | 4 | Accept
4 | Lack of suitable champion and sponsor |  |  | Stakeholder | Possible | Extreme | Unlikely | Extreme | 15 | 10 | Mitigate
5 | Lack of qualified bidders |  |  | Procurement | Possible | High | Unlikely | Medium | 12 | 6 | Accept
6 | Business analysis resources unavailable |  |  | Human Resources | Probable | High | Possible | High | 20 | 12 | Mitigate

## Lookups (hidden)
Risk Category | Meaning | Risk Responses | Meaning |  | Impact | Meaning | Val
Financial | Risk pertains primarilyy to project funding or budget | Accept | To accept a risk means that you are not actively doing anything to reduce the probability or impact. You might still be monitoring the risk, symptoms, events, etc… |  | Negligible | Few discernible effects on project outcomes | 1
Schedule | Risk pertains primarily to project schedule, milestones and deadlines | Mitigate | To mitigate a risk means that you are actively trying to reduce the probability and/or impact through a variety of risk responses. |  | Low | Minor effects on project outcomes | 2
Procurement | Risk pertains premarily to the procurement process and vendor management | Avoid | To avoid a risk means that you are trying to eliminate the risk altogether by making some critical change to the project (reducing scope to eliminate a dependency) |  | Medium | Moderate effects on project outcomes | 3
Requirements | Risk pertains primarily to requirements, use cases, functionality, technical feasibility, etc… | Transfer | To transfer a risk means to transfer or share a risk with another party. Insurance, outsourcing, fixed price contracts, etc… are risk transfer methods. |  | High | Major effects on project outcomes | 4
Stakeholder | Risk pertains primarily to business engagement, stakeholder management, public perception |  |  |  | Extreme | Critical effect on project outcomes | 5
Quality | Risk pertains primarily to project quality, conformance, etc… | Likelihood | Meaning | Val
Human Resources | Risk pertains primarily to the project team and project human resources. | Remote | 0-10% likelihood | 1
|  | Unlikely | >10-25% likelihood | 2
|  | Possible | >25-50% likelihood | 3
|  | Likely | >50-90% likelihood | 4
|  | Probable | >90% likelihood | 5

## Risk Heat Map
Extreme | 0 | 1 | 0 | 0 | 0
High | 1 | 0 | 1 | 1 | 0
Medium | 0 | 1 | 0 | 0 | 0
Low | 0 | 1 | 0 | 0 | 0
Negligible | 0 | 0 | 0 | 0 | 0
| Remote | Unlikely | Possible | Likely | Probable

## Residual Risk
Extreme |  | 0→1 | 1→0
High | 0→1 |  | 2→1 | 1→1 | 1→0
Medium |  | 0→1 | 1→0
Low |  | 0→1
Negligible
| Remote | Unlikely | Possible | Likely | Probable